# 3-year PhD Project Timeline — NGO accountability

## Months 1-6

Literature review; refine research questions; PhD training modules.

## Months 6-9

Finalize methodology; ethics approval application.

## Months 9-12

Pilot study; first-year progression review; conference abstract.

## Months 12-20

Main data collection.

## Months 20-26

Data analysis; first journal article submission.

## Months 26-32

Thesis writing; second paper; international conference presentation.

## Months 32-36

Final drafts, submission, viva preparation.

## Standing milestones

Supervisor meetings every 2 weeks

Annual progression reviews

Ethics approval before any data collection

Target: 1 conference + 1 journal submission per year (adjust per field)